## Gantt
Task | 2019-07-08 | 2019-07-15 | 2019-07-22 | 2019-07-29 | 2019-08-05 | 2019-08-12 | 2019-08-19 | 2019-08-26 | 2019-09-02 | 2019-09-09 | 2019-09-16 | 2019-09-23 | 2019-09-30 | 2019-10-07 | 2019-10-14 | 2019-10-21 | 2019-10-28 | 2019-11-04 | 2019-11-11 | 2019-11-18 | 2019-11-25 | 2019-12-02
Phase 1 - Prepare Historic Data
Find Data Sources
Create Script to test
Determine Data Source
Clean Data Set
Create Training/Test Sets | bar: 2019-07-15
Phase 2 - Create Model
Create Training Script | bar: 2019-07-15
Initial Script Testing | bar: 2019-07-22
Phase 3 - Refine Model
Time Step Length Study | bar: 2019-07-29
Training Time:Prediction Time Ratio Study | bar: 2019-08-05 to 2019-08-12
Overlapping Models Study | bar: 2019-08-19 to 2019-09-02
Multiple FOREX Pairs Study | bar: 2019-08-26 to 2019-09-02
Phase 4 - Create Live Architecture
Edit Exisiting Script | bar: 2019-07-08
Create Live Data Logger | bar: 2019-07-08 to 2019-07-15
Create Live Communicator | bar: 2019-07-22 to 2019-08-12
Integrate Live Modules with Model | bar: 2019-08-19
Test Architecture | bar: 2019-08-26 to 2019-09-02
Phase 5 - Go Live | bar: 2019-09-09

## To-Do
Coding |  | Non-Coding
Data Logging Module |  | Data Logging Module
Write patcher to in-fill missing data points
Prediction Module |  | Prediction Module
| Write base prediction module |  | Define variable values
Define epics to model
Explore use of multiple epics in one model
Indicator Module |  | Indicator Module
| Write indicators module |  | Define architecture for data visualisation
| Write data visualisation |  | Define epics to analyse
Other |  | Other
| Write historic data graph creator |  | Setup FTPS Users
| Create live visualisation for trading |  | Setup eToro account
Setup Ltd partnership?